# Preliminary Risk and Security Log

Part 1: Risk Assessment Key

| Score | Likelihood (1–5) | Impact (1–5) |
| --- | --- | --- |
| 1–4 | Low: Keep under review. | Minor: Inconvenient but not critical. |
| 5–12 | Medium: Needs a plan. | Moderate: Requires changes to design/code. |
| 15–25 | High/Extreme: Urgent action required. | Catastrophic: Project failure / Data Breach. |

Part 2: Risk Register — PM Role Specific Risks

| Ref ID | Risk Category | Risk Description / Threat | Likelihood (1–5) | Impact (1–5) | Total Score (L x I) | Proposed Mitigation for Sprint 2 |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | Schedule | Team member submits Sprint 2 work late — causing the check-in or rewards feature to be incomplete at sprint review | 3 | 4 | 12 — Medium | Daily Basecamp check-ins flag delays within 24 hours. Excel tracker reviewed each morning. PM escalates and reallocates tasks if any item is 2+ days overdue. Mid-sprint Google Meet confirms progress against plan. |
| R02 | Technical | Node.js API fails to connect correctly to MySQL database — blocking frontend UI from displaying live data | 3 | 5 | 15 — High | Database connection tested in isolation before frontend integration. Connection string stored in .env file (not hardcoded). Udara and Pulindu to do a joint integration test at the start of Sprint 2 before new features are built. |
| R03 | Security | Student passwords or database credentials accidentally committed to GitHub repository in plain text | 2 | 5 | 10 — Medium | .env file added to .gitignore from Sprint 1. All team members briefed: no credentials in code. PM to scan repository for exposed secrets before each sprint review using GitHub secret scanning. bcrypt used for all passwords in MySQL. |
| R04 | Team | Merge conflicts on GitHub — two developers edit the same HTML or Node.js file simultaneously, breaking the integration branch | 4 | 3 | 12 — Medium | Enforced feature branch strategy — no direct commits to dev or main. All merges via Pull Request reviewed by PM before merge. Team members instructed to pull latest dev before starting each session. PM monitors open PRs daily. |
| R05 | Schedule | Scope creep — features planned for Sprint 3/4 (social feed, notifications) are started in Sprint 2, leaving core check-in and rewards work incomplete | 3 | 3 | 9 — Medium | Sprint backlog reviewed at every standup and Google Meet. Any out-of-scope work is immediately moved to a future sprint backlog item on Basecamp. PM enforces sprint boundaries strictly — occurred once in Sprint 1, resolved in mid-sprint review. |